## Sheet1
S.No. | Activity | Start Date | Completion Date | Status | Remarks | Notes
Week starting 3rd Dec
1 | registration for the Andrew NG machine learning course and introduction | 8th dec | 8th dec | completed
2 | motor code and algorithm | 5th dec | ------------------- | ongoing | various methods were checked and yet to achieve the most generalised algorithm to optimise the memory used and time taken to execute
3 | linear regressions from the course | 9th dec | 9th dec | completed
4 | gradient descent | 9th dec | 9th dec | completed | gradient descent completed with fair ease as methods are similar to the various numerical methods taught in math
5 | Linear Algebra Review | 10th Dec | 10th Dec | completed | basic matrix operations were retaught
6 | Week 2 of course starts | 10th dec | 14th Dec | completed
7 | basics of machine learning with respect to univariate linear regression | 10th dec | 12th Dec | completed
COMPLETED
| ######################################################### | ########### | ################# | ############## | ############################## | ##########################
week starting 11 Dec 2018 | [5 empty] | note: I fell sick and so some tasks were delayed
1 | application of univariate linear regressions for simple examples (week 2 completed) | 11th Dec | 15th Dec
2 | motor code and algorithm (worked on further. hope to be completed by next week) | 11th Dec | 11th Dec | algorithm and first code complete | currently, the motor code consists of the simplest algorithm constituting of switch cases and if statements | The previous algorithm was trashed as the memory taken up was too high
3 | gradient descent and normal equation application | 11th Dec | 17th Dec | completed | both methods have been completed. normal equations method has been tested for one and two variables
4 | testing of motor code | 16th Dec | ---------------------- | ongoing
5 | week 3 of course (logistic regression) | 16th Dec | ---------------------- | ongoing
COMPLETED
############# | ######################################################### | ############# | ################### | ############## | ############################## | ##########################
week starting 17th Dec 2018 | [5 empty] | working on a better motor code algorithm. yet to test basic algorithm
1 | logistic regression application | 18th Dec | 20th Dec | completed | completed and code has been uploaded
2 | week 4 starts | 21st Dec | 22nd Dec |  | prediction using forward propagation was completed in octave. python implementation is left | Working on selection of project. mostly an object detection program or a handwriting detection program as in the course
3 | week 5 starts | 22nd Dec | ongoing | ongoing | back propagation algorithm is taking a while