## Sheet1
Week Starting 3 Dec 2018 | [5 empty] | note: the week was started late as the wrong course had been started (problems with manipal global program).
S.No. | Activity | Start Date | Completion Date | Status | Remarks
1 | registration for the Andrew NG machine learning course and introduction | 8th dec | 8th dec | completed
2 | motor code algorithm and code for quadrant 2 | 5th dec | ------------------- | ongoing | various methods were checked and yet to achieve the most generalised algorithm to optimise the memory used and time taken to execute
3 | linear regressions from the course | 9th dec | 9th dec | completed
4 | gradient descent | 9th dec | 9th dec | completed | gradient descent completed with fair ease as methods are similar to the various numerical methods taught in math
5 | Linear Algebra Review | 10th Dec | 10th Dec | completed | basic matrix operations were retaught
6 | Week 2 of course starts | 10th dec | --------------------
7 | basics of machine learning with respect to univariate linear regression | 10th dec | -------------------- | ongoing
week starting 11 Dec 2018 |  |  | hopeful completion date
1 | application of univariate linear regressions for simple examples | 11th Dec | 13th Dec
2 | motor code and algorithm (worked on further. hope to be completed by next week) | 12th Dec | 17th Dec
3 | gradient descent and normal equation application | 11th Dec | 15th Dec